{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":40,"n_cols":5,"rows_kept":40,"merged":[[0,0,0,3],[20,0,20,4]],"flags":["formulas_cached_only"]}
["上周计划（03.09 - 03.14）",{"$nulls":3},"完成情况"]
["功能","内容描述","执行人","配合人"]
["万家热线技术对接","万家热线对接券码生成、对接商品后台管理，门店端核销接口对接、","陈海波","王芳、李杰、嘉慧、李祥新、刘兵","是"]
["合肥市集对接","和合肥市集沟通对接并技术实现","陈海波","王芳、李杰、李祥新、刘兵","否"]
["退款功能","伊莎小程序可以申请退款，后台可以直接退款（包含微信退款）","李杰","刘兵","是"]
["小程序、门店端补款接口对接","用户下单价格需要补款的","王芳、李杰","李祥新、刘兵","否"]
["物流分配地图优化","关闭后重新打开显示所有已划过的区域（不明白的问我，要求精细化确定区域，并且画一个区域的同时，把之前已划过的显示出来）","李杰",null,"是"]
["评论有奖发放","公众号评论发奖","李杰",null,"是"]
["顺丰对接跟踪","顺丰整个流程走通","王芳","技术部配合测试","是"]
["惠生活对接测试","bug修改","李跃文","陈海波、李杰配合调试（总经办有安卓手机并且是移动号的配合测试）","否"]
["小马哥取衣界面优化","显示衣物详情","李杰、刘兵",null,"是"]
["手机版本物流分配","app新增功能，手机可以分配小马哥","李祥新、王芳，嘉慧",null,"否"]
["支付界面优化","可以增减商品","王芳、刘兵",null,"否"]
["前端工作对接","本周李跃文和刘兵对接完前端所有工作","刘兵、李跃文",null,"是"]
["后台首页数据图形化展示","参考右图，具体展示讨论（echats）","李杰",null,"否"]
["收衣app网络订单录入功能",null,"李祥新",null,"是"]
["收衣app蓝牙打印",null,"李祥新",null,"否"]
["用户下单推送消息优化","点击公众号消息跳转到制定界面（如小马哥，衣物详情）","王芳",null,"是"]
["小票余额不显示",null,"王芳、李祥新",null,"？"]
["用户下单自送门店免运费功能接口对接",null,"王芳、刘兵",null,"是"]
["本周工作（3.16-3.20）"]
["功能","内容描述","执行人","配合人","时间"]
["合肥市集对接","合肥市集沟通具体方案，并技术实现","王芳","陈海波","周一下班前"]
["小程序、门店端补款接口对接","用户下单价格需要补款的","王芳","李祥新、刘兵、李杰","周三"]
["小票余额不显示、备注错乱",null,"李祥新","王芳","周二下班前"]
["公众号小程序认证",null,"李杰",null,"周四上午"]
["惠生活对接测试正式上线","bug修改","陈海波","刘兵、李杰","周二下班前"]
["后台首页数据图形化展示","参考右图，具体展示讨论（echats）","李杰",null,"周二下班前"]
["收衣app蓝牙打印、更新，测试等所有功能结束",null,"李祥新",null,"周三下班前"]
["近期营销活动商讨确定",null,"嘉慧",null,"周二下班前"]
["所做项目的重要功能操作手册","工厂端操作手册（陈海波）、小程序下单操作手册、网单录入（王芳）、小马哥操作手册（李杰）、[陈海波提供模板，大家商讨]",null,null,"周三下班前"]
["小马哥点击详情查看不了衣物详情",null,"刘兵","李杰","周一上午"]
["伊莎小程序支付逻辑优化（运费、折扣、团体）",null,"王芳","陈海波、刘兵","周四下班前"]
["门店端首页公司公告、和待办事项",null,"李祥新","李杰","周一"]
["门店端通过时间段查询沉默用户",null,"李祥新","李杰","周三"]
["顺丰流程跑通继续测试",null,"王芳","技术部","周二"]
["熟悉前后端和数据库设计，并从自己的角度考虑优化思路",null,"刘兵",null,"周四下班前"]
["后台所有功能分类规划",null,"陈海波",null,"周三下班前"]
["已做项目开始部署优化","从数据库到代码段，制定规则优化","陈海波",null,"规则制定、周四下班前"]
["今年公司项目发展方向确定并形成文档",null,"总经办",null,"看时间待定"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}